# Activity 1 – The Production Schedule

| Key dates and deadlines |  |  |  |
| --- | --- | --- | --- |
| PRELIMINARY Weeks 1-2 | Begin log/blog | Start research and planning | Learn to use equipment. Produce preliminary production |
| Week 3 | Record self-evaluation in log/blog | Consider how to use similar ideas in actual production | Peer group assessment & evaluation of preliminary productions |
| PRODUCTION Weeks 3-6 | Details recorded | Research representation, target audience. Plan details. Detailed research and planning completed | Write Statement of Intent, deliver pitch & evaluate feedback Evaluate and assess peers' plans and Statements of Intent |
| Weeks 7-10 | Continue blog | Production gets underway |  |
| Week 8 Interim deadline 1 | Record peer evaluation and own response | Complete first stage of production | Check peers' work for requirements, media language, representation |
| Weeks 9-11 |  | Production continues | Test on target audience |
| Week 12 Interim deadline 2 | Record peer evaluation and own response | Complete second stage of production | Check peers' work for detailed requirements, media language, representation and audience |
| Weeks 13-15 |  | Production continues |  |
| Week 16 Final deadline | Record peer evaluation | Finish production | Final peer review |
| Week 17 Finish |  | Make small final adjustments Production completed. |  |